MASTERING READY

90-Day Execution Calendar

Day-by-Day  |  Week-by-Week  |  Task-by-Task

Split: 70% Engine B (LATAM)  /  30% Engine A (US/EU)

Max daily time: 1.5–2 hours marketing  |  Budget: $50–200/mo

TikTok: Parked until Month 2  |  Instagram: Personal + @masteringready

February 2026  |  Prepared for Sara

# How to Use This Calendar

Each week has a single goal, daily tasks with engine labels and time estimates. The total daily marketing time should stay under 2 hours. If a day feels overloaded, push the Engine A task to the next day — Engine B always takes priority in Month 1.

| Engine B | LATAM/Spain. Facebook groups, Instagram ES, WhatsApp, YouTube ES creators. 70% of effort. |
| --- | --- |
| Engine A | US/Canada/EU. Reddit, English content, forums. 30% of effort. |
| Both | Infrastructure tasks that serve both engines (pixel, accounts, analytics). |
| Time estimates | Per task. A 30-min day = focused sprint. A 90-min day = heavier but manageable. |

# MONTH 1: Signal Acquisition

Goal: 25–40 registered users. Budget: $0–70. Focus: Build presence, seed communities, get first real users.

Month 1 is almost entirely organic. No ads until Week 4. The work is showing up, being helpful, and putting the product in front of people who are already asking for it.

WEEK 1: Foundation  (Feb 17–23)

WEEK GOAL: Instagram set up, FB groups mapped & joined, first 3 Spanish Reels posted, Reddit presence started. 5 real producers run their first analysis.

| Day | Engine | Tasks | Time |
| --- | --- | --- | --- |
| Mon | Both | Install Meta Pixel on masteringready.com (both ES and EN pages) Create @masteringready Instagram. Bio: bilingual. Profile pic: logo. Link: masteringready.com Verify Google Search Console is active for masteringready.com | 45 min |
| Tue | Engine B | Facebook group mapping. Search: "Producción Musical," "Mezcla y Mastering," "Home Studio," "FL Studio Español," "Beatmakers." Join top 8–12 groups Introduce yourself in 2–3 groups (one short post each: engineer/producer in Colombia) | 60 min |
| Wed | Engine B | Record Reel #1 (ES): Score Reveal. Screen-record a real analysis. Narrate naturally: what you uploaded, what score it got, one thing you’d fix. 30–45 seconds Post from personal IG, tag @masteringready. Cross-post to @masteringready | 60 min |
| Thu | Engine A | Reddit: Browse r/mixingmastering and r/WeAreTheMusicMakers. Answer 2–3 questions about mixing/mastering. No mention of MR. Just helpful, technical answers Answer 2–3 questions in ES Facebook groups (same approach — value only) | 45 min |
| Fri | Engine B | Record Reel #2 (ES): Before/After. Show a rough mix analysis → explain one fix → re-analyze. Show score improvement Post from personal IG + @masteringready. Share in 1–2 FB groups as a video post (not just link) | 60 min |
| Sat | Engine B | Ask 3–5 producer friends to try MR. Include 2+ LATAM-based. Ask them to screenshot their score and post on Stories tagging @masteringready Join 1–2 WhatsApp producer groups (find links in FB groups or gruposwats.com) | 30 min |
| Sun | Engine B | Record Reel #3 (ES): Education Drop. Pick one metric (headroom, PLR, stereo width). Explain it using a real MR report. Keep it under 60 seconds Post everywhere: personal IG, @masteringready, 1–2 FB groups | 45 min |

CHECKPOINT: By Sunday: @masteringready exists, 3 Reels posted, 8–12 FB groups joined, Reddit presence started. If any of these didn’t happen, they’re Monday’s priority.

WEEK 2: Consistency  (Feb 24–Mar 2)

WEEK GOAL: Posting rhythm established. 3 more Reels (ES). Reddit karma building. FB group presence growing. First 5–10 organic signups.

| Day | Engine | Tasks | Time |
| --- | --- | --- | --- |
| Mon | Engine B | Answer 3–5 questions in FB groups. Look for "is my mix ready" or "should I pay for mastering" style posts Post value content in 1 FB group: a tip about headroom, gain staging, or LUFS — no MR mention | 40 min |
| Tue | Engine A | Reddit: Answer 3–4 questions across r/mixingmastering, r/audioengineering, r/edmproduction. Build karma and visibility | 30 min |
| Wed | Engine B | Record Reel #4 (ES): Analyze a well-known track in a LATAM genre (reggaeton, cumbia, trap latino). Show the score, react to results Post across all channels. Share in 2–3 FB groups as native video | 60 min |
| Thu | Both | Check analytics: How many anonymous analyses? How many signups? Which Reels performed best? Note what’s working Answer questions in both Reddit (2–3) and FB groups (2–3) | 40 min |
| Fri | Engine B | Record Reel #5 (ES): "The Challenge" format. Analyze your own mix, post the score, challenge followers to beat it DM 1–2 ES YouTube creators (mid-tier, 5K–50K subs who teach mixing). Short genuine message, offer free Pro account | 50 min |
| Sat | Engine A | Post 1 EN Reel on @masteringready: repurpose your best-performing ES Reel concept but in English | 30 min |
| Sun | Engine B | Record Reel #6 (ES): Another Score Reveal, different genre than previous ones. Variety shows the tool works across styles Share in any WhatsApp groups you’ve joined. Natural mention: "I just ran my latest mix through this, here’s what it found" | 40 min |

CHECKPOINT: By Sunday: 6 ES Reels + 1 EN Reel posted. Consistent daily presence in FB groups and Reddit. First organic signups should be appearing. Check admin dashboard.

WEEK 3: Launch Posts  (Mar 3–9)

WEEK GOAL: Builder launch post on Reddit. Tool announcement in top FB groups. First influencer outreach response. Target: 15–20 cumulative signups.

| Day | Engine | Tasks | Time |
| --- | --- | --- | --- |
| Mon | Engine B | Write FB group launch post (ES). Frame: "Construí una herramienta gratuita que analiza tu mezcla y te dice si está lista para mastering. Sin guardar tu audio. En español. Les comparto el link y me cuentan qué les parece." Post in your #1 most active FB group. Respond to every comment within 2–3 hours | 60 min |
| Tue | Engine B | Post launch message in 2–3 more FB groups (adapt slightly per group culture) Follow up on influencer DMs from last week. Send 1–2 new DMs | 45 min |
| Wed | Engine A | Write Reddit launch post. Title: "I built a free tool that tells you if your mix is ready for mastering — no audio stored. Looking for feedback." Post in r/WeAreTheMusicMakers Monitor and respond to every comment for the rest of the day | 90 min |
| Thu | Both | Respond to all launch post engagement (Reddit comments, FB comments). This is your highest-ROI activity today Record Reel #7 (ES): Show the response to the launch. "Les compartí la herramienta ayer, miren lo que me dijeron." Social proof content | 60 min |
| Fri | Engine B | Post launch message in remaining FB groups (2–3 more). Post in WhatsApp groups Boost your best-performing ES Reel ($10–20, target music production interests in MX/CO/AR) | 40 min |
| Sat | Engine A | Post in KVR Audio or Gearspace forums: product announcement thread. Frame as "built this for my own workflow, sharing in case useful" | 30 min |
| Sun | Both | Week 3 data review. Pull numbers: total signups, analyses run, top traffic sources (UTM), which launch posts got most engagement. Write 3 bullet summary of what’s working and what’s not | 30 min |

CHECKPOINT: By Sunday: Launch posts live on Reddit + 5–8 FB groups + 1–2 forums. If signups aren’t hitting 15+, diagnose: is it traffic (not enough reach) or conversion (traffic but no signups)?

WEEK 4: First Ads + Iteration  (Mar 10–16)

WEEK GOAL: First paid ads live (both engines). Content iteration based on data. Target: 25–40 cumulative signups. Budget: $30–50 this week.

| Day | Engine | Tasks | Time |
| --- | --- | --- | --- |
| Mon | Engine B | Launch ES Meta ad. Use best-performing Reel as creative. Budget: $2–4/day. Target: MX, CO, AR, CL, PE. Interests: producción musical, FL Studio, Ableton. Optimize for link clicks Continue answering FB group questions (2–3 answers) | 60 min |
| Tue | Engine A | Launch EN Meta ad. Budget: $3–5/day. Target: US/CA/UK/AU. Interests: mixing, mastering, audio engineering, DAWs. Use best EN content or repurposed ES Reel Reddit: Answer 2–3 questions. Naturally mention MR where relevant ("try running it through Mastering Ready first") | 50 min |
| Wed | Engine B | Record Reel #8 (ES): Analyze a famous reference track (pick something your audience cares about). Post results as educational content Post in FB groups as value content + share on @masteringready | 50 min |
| Thu | Both | Check ad performance (both campaigns). After 3 days: which has lower cost per click? Which has more signups? Don’t change anything yet — just observe Respond to community (Reddit + FB groups, 15 min each) | 40 min |
| Fri | Engine B | Record Reel #9 (ES): Price reveal content. "Análisis profesional a $5.49/mes en Colombia — 20,100 pesos." Show the pricing page in local currency DM 2 more ES YouTube creators. Follow up on any previous responses | 50 min |
| Sat | Engine A | Record 1 EN Reel. The "Famous Mix Analysis" concept in English. Cross-post to @masteringready | 30 min |
| Sun | Both | Month 1 review. Compile: total signups per engine, analyses run, ad spend, cost per signup, top traffic sources. Identify: which engine has more traction? Which content type performs best? Any paid conversions yet? Decision: adjust Month 2 budget split based on data | 45 min |

CHECKPOINT: MONTH 1 COMPLETE. Key question: where are the signups coming from? If Engine B dominates, go 80/20 in Month 2. If mixed, stay 70/30. If Engine A surprises, shift to 60/40.

# MONTH 2: Amplification + Conversion Layer

Goal: 40–70 cumulative users, first 5–10 paying. Budget: $100–150. New priority: build the email onboarding sequence that converts free users to paid.

Month 2 adds two things: scaled ads on the winning engine, and the email layer that was missing from Month 1. Content production continues at the same pace (3 Reels/week). Community presence becomes maintenance, not new seeding.

WEEK 5: Scale Winning Engine + Email Build  (Mar 17–23)

WEEK GOAL: Scale winning ad. Build email welcome sequence. TikTok evaluation. Continue content rhythm.

| Day | Engine | Tasks | Time |
| --- | --- | --- | --- |
| Mon | Both | Scale winning ad to $5–7/day. Kill underperforming ad. If both work, keep both but shift budget 70/30 Start email welcome sequence build. Email 1: "Welcome — here’s how to get the most from your analysis" (bilingual). Use Supabase or whatever email system is available | 90 min |
| Tue | Engine B | Record Reel #10 (ES). Continue the rhythm. 3/week, ES-first FB groups: maintenance. Answer 2–3 questions, share Reel in 1 group | 45 min |
| Wed | Both | Build Email 2: "Your mix scored [X] — here’s what your score means." Triggered 24h after first analysis. Include one improvement tip per score range Evaluate TikTok: If ES Reels are getting strong engagement on IG, cross-post top 3 to TikTok. If not, stay parked | 60 min |
| Thu | Engine A | Reddit: Post in a new sub (r/edmproduction or r/audioengineering) if you haven’t yet. Share a genuine insight, mention MR naturally Answer 2–3 questions | 30 min |
| Fri | Both | Build Email 3: "You’ve used your free analyses — here’s what Pro gives you." Conversion email. Triggered after 2 free analyses used. Include price in local currency if possible Record Reel #11 (ES) | 60 min |
| Sat | Engine B | Check if any YouTube creator has posted a review. Share/amplify if yes. Follow up on pending DMs | 20 min |
| Sun | Both | Review ad metrics. Cost per signup, CTR, landing page conversion. Adjust targeting if needed Record EN Reel or repurpose best ES Reel for English audience | 40 min |

WEEK 6: Product Hunt Prep + Challenge Launch  (Mar 24–30)

WEEK GOAL: "Post Your Score" challenge launched. Product Hunt prepped. Email sequence live. First paid conversions expected.

| Day | Engine | Tasks | Time |
| --- | --- | --- | --- |
| Mon | Both | Email sequence goes live. Test with your own account first. Verify trigger timing and content in both languages Launch "Post Your Score" challenge in FB groups (ES) and on IG. Create shareable Story template | 60 min |
| Tue | Engine B | Promote challenge in 3–5 FB groups and WhatsApp groups Record Reel #12 (ES): Show challenge entries, react to scores | 45 min |
| Wed | Engine A | Prep Product Hunt listing. Write tagline, description, 2-min demo video script. Line up 10–20 supporters to upvote on launch day | 60 min |
| Thu | Engine B | Content + community maintenance. Answer questions, share challenge results, post Reel #13 (ES) | 40 min |
| Fri | Both | Check conversion data. Any free → paid? Which country? Which referral source? This data shapes Weeks 7–12 Record Product Hunt demo video (EN, 2 minutes) | 50 min |
| Sat–Sun | Both | Finalize Product Hunt listing. Schedule for early next week Weekend Reel (ES or EN based on what’s needed) | 45 min |

WEEK 7: Product Hunt + Retargeting  (Mar 31–Apr 6)

WEEK GOAL: Product Hunt launch. Add retargeting campaign. Reach 50+ cumulative signups.

| Day | Engine | Tasks | Time |
| --- | --- | --- | --- |
| Mon–Tue | Engine A | Product Hunt launch day. Post early AM. Respond to every comment. Share on Reddit, Twitter/X, LinkedIn. Push hard for 24 hours | 2–3 hrs launch day |
| Wed | Both | Launch retargeting campaign on Meta. Target: website visitors who didn’t sign up. Budget: $2–3/day. Creative: "You analyzed your mix — ready to see the full report?" | 45 min |
| Thu–Fri | Engine B | Back to Engine B rhythm. 2 Reels, FB group activity, influencer follow-ups Reach out to LATAM mastering studios via WhatsApp: "Send your clients to MR before they send you their mixes" | 40 min/day |
| Sat–Sun | Both | Post-PH analysis. How many signups? How many stuck? Any paid? What feedback came in? Record 1–2 Reels. Capitalize on any PH momentum | 30 min/day |

WEEK 8: Optimize + Double Down  (Apr 7–13)

WEEK GOAL: Month 2 wrap-up. Reach 60–70 cumulative signups, 5–10 paid. Decide Month 3 engine allocation.

| Day | Engine | Tasks | Time |
| --- | --- | --- | --- |
| Mon–Wed | Both | Optimize ads. Kill losing audiences. Double budget on winning segments. Test 1 new creative per engine Content rhythm continues: 2–3 Reels/week, FB groups, Reddit | 45 min/day |
| Thu | Engine B | Second wave FB group posts in groups you haven’t launched in yet, or re-post with updated angle (testimonials, challenge results) | 40 min |
| Fri–Sun | Both | Month 2 retrospective. Full data pull: signups by engine, signups by country, paid conversions, cost per signup by channel, email open rates, ad ROAS. Write 1-page summary Set Month 3 budget allocation based on which engine won | 90 min total |

CHECKPOINT: MONTH 2 COMPLETE. By now you should know: which engine drives signups, which drives revenue, and whether they’re the same engine. If LATAM signups are high but paid is low, that’s the DLocal signal. If both are low, revisit product positioning.

# MONTH 3: Optimization + First Revenue Milestone

Goal: 100+ cumulative users, 15–25 paid, $100–200 MRR. Budget: $100–200. Engine split: based on Month 2 data (likely 70–80% toward winning engine).

Month 3 is about turning signal into revenue. The playbook is simpler: keep doing what works, cut what doesn’t, and add the referral/testimonial layer.

WEEK 9: Revenue Push  (Apr 14–20)

WEEK GOAL: Focus on conversion. Optimize email sequences. Target 10+ paid users. Collect first testimonials.

| Day | Engine | Tasks | Time |
| --- | --- | --- | --- |
| Mon | Both | Review email sequence performance. Open rates, click rates, conversion to paid. Rewrite subject lines for underperforming emails Add Email 4: Re-analysis reminder. "It’s been 2 weeks since your last analysis. Upload your latest version." Triggered for inactive registered users | 60 min |
| Tue–Wed | Both | Content continues on winning engine: 2 Reels, community presence Ask 3–5 existing users for testimonials. Short quote + permission to use. Bilingual | 40 min/day |
| Thu | Both | Optimize ads. Create country-specific ad sets if one LATAM country dominates. Or create audience-specific EN ads if one interest group converts better | 45 min |
| Fri–Sun | Both | Create testimonial content. Turn user quotes into Reels, FB posts, and ad creative Publish 1 blog post (SEO) in winning engine’s language. Target: "is my mix ready for mastering" or "cómo saber si mi mezcla está lista" | 60 min total |

WEEK 10: Scale What Works  (Apr 21–27)

| Day | Engine | Tasks | Time |
| --- | --- | --- | --- |
| All week | Both | Winning engine gets 80% of time. Maintain the rhythm: 3 Reels, community answers, ads running, email sequence converting Losing engine gets maintenance mode: respond to comments, let ads run at minimum viable spend or pause Test 1 new ad creative with testimonial content Collect 2–3 more testimonials | 45 min/day avg |

WEEK 11: Referral Prep + Push to 100  (Apr 28–May 4)

| Day | Engine | Tasks | Time |
| --- | --- | --- | --- |
| Mon–Wed | Both | Design simple referral mechanic. "Give a friend 2 free analyses, get 2 yourself." Even if not automated, do it manually via email for now Push referral to existing users via email: "Know someone who’d find this useful? Forward this email" Content continues: 2–3 Reels/week | 60 min/day |
| Thu–Sun | Both | Final push to 100 users. What’s the gap? If 80 users, you need 20 more. Calculate: at current cost per signup, how much ad spend closes the gap? Allocate remaining budget accordingly If Engine B LATAM signups high but paid low: Evaluate DLocal priority. Document the conversion gap for your own roadmap | 45 min/day |

WEEK 12: Review + Plan Next Phase  (May 5–11)

| Day | Engine | Tasks | Time |
| --- | --- | --- | --- |
| Mon–Wed | Both | 90-day retrospective. Full data pull across both engines: - Total users, paid users, MRR, churn - Cost per signup by engine, by channel, by country - Best-performing content, best-performing ad creative - Email sequence conversion rates - Testimonial library | 2 hours total |
| Thu–Sun | Both | Write Month 4–6 plan based on what you now know. Key decisions: - Which engine gets primary investment? - Is DLocal the #1 priority for LATAM conversion? - Budget increase to $300–500/mo viable? - Referral program worth automating? - YouTube channel worth starting? - Stream Ready cross-promotion timing? | 2 hours total |

CHECKPOINT: 90 DAYS COMPLETE. If you hit 100 users and $100+ MRR, you have product-market fit signal. If you hit 100 users but <$50 MRR, you have a conversion problem (likely payment methods or email sequence). If you’re under 50 users, revisit positioning and channel strategy.

# Daily Rhythm Cheat Sheet

On any given day, your marketing work fits into one of three modes. Pick the mode, do the work, stop. No context-switching between modes.

|  | Light Day (30 min) | Medium Day (60 min) | Heavy Day (90 min) |
| --- | --- | --- | --- |
| Community | Answer 2–3 questions (FB or Reddit) | Answer 3–5 questions + 1 value post | Launch post or challenge + respond to all comments |
| Content | Cross-post existing Reel to another platform | Record + post 1 new Reel | Record Reel + write blog post or create ad creative |
| Ops | Check ad spend + performance | Check analytics + adjust 1 campaign | Full data review + strategic decision |

# Content Bank: Reel Ideas to Never Run Out

Rotate through these. Each can be done in either language. You need 3/week — this list covers 8+ weeks:

| # | Format | Concept |
| --- | --- | --- |
| 1 | Score Reveal | Upload a mix → show the score → react |
| 2 | Before/After | Analyze → fix one thing → re-analyze → show score improvement |
| 3 | Education Drop | Explain one metric (headroom, PLR, stereo width, crest factor) using a real report |
| 4 | Famous Track | Analyze a well-known reference track. Show what "mastering-ready" actually looks like |
| 5 | The Challenge | Post your score, challenge followers to beat it |
| 6 | Price Reveal | Show local currency pricing. "$5.49/mes = 20,100 COP" |
| 7 | How It Works | 60-second screen recording walkthrough. The "tutorial" that’s also marketing |
| 8 | Genre Battle | Analyze same song in different genres. Which style scores highest? |
| 9 | User Score | Repost a follower’s score (with permission). React and give one tip |
| 10 | Myth Bust | "You don’t need expensive gear to get a good score." Analyze a phone-recorded track |
| 11 | The PDF | Show the full PDF report. Walk through what each section means |
| 12 | Builder Story | "Why I built this." Your origin story as an audio engineer who got tired of guessing |
| 13 | Common Mistakes | "The #1 reason mixes fail the analysis." Show real data from your own mixes |
| 14 | Testimonial | User quote + their score + before/after story |
| 15 | Privacy Angle | "We analyze your mix and forget it existed." Show the tech behind no-audio-storage |

Execute the week. Review the data. Adjust the next week. Repeat.